## Slide 1: Presentation
E-commerce(shoes)
Project Management

## Slide 2: Chartet
*Project name : E-commerce(shoes)
*Project sponser : Dark store
*Title : assuit _alnemas street Egypt
*the phone : 043339256
*E-mail : darkstore@gmail.com
*Project manager :mr/Mohamed Salah

## Slide 3: Team
عبدالله محمد عبدالسيد حسين
عبدالرحمن زكريا سنوسي خالد

## Slide 4: Description
As a result of the process of development in the Internet had to be marketing to get a share of the advantages of this so our project works on marketing (shoes) in an easy and fast way for users where they can buy and pay in several different ways to facilitate them

## Slide 5: Project objective
: As a result of the process of development in the Internet had to be marketing to get a share of the advantages of this so our project works on marketing (shoes) in an easy and fast way for users where they can buy and pay in several different ways to facilitate them

## Slide 6: Requirement
1-web site
2-data base
3-buy chose
4-research

## Slide 7: constraints
Are anything that limited the project manager’s options Project constraints include:  Budgets: The project cost mustn’t exceed the range of 200.000$  Deadline: The project must be done by the begin of the next year  Resources: *The system hardware devices must all be from DELL *The system software licenses must be accredited from Oracle *Servers must upload the database on the cloud

## Slide 8: Project Assumptions
1-every person can find us in neternet
2-No one will leave the team
3-the payement will be in cash only
4- no showing product not exsit in the campny

## Slide 9: WBS
      1.1 Initiation
      1.2-Software &Hard ware
1.2.1 Install
1.2.2 Design
1.2.3 Implement
      1.3- test web
      1.3.1-unit test
      1.3.2-system test
      1.4- Close

## Slide 10: Budget
ID | DUR | TASKS | Budget
1.1 | 7 | Initiation | 40,000$
1.2.1 | 1 | Soft &hard ware install | 20,000
1.2.2 | 2 | soft& hard ware design | 45,000
1.2.3 | 3 | soft& hard ware implement | 40,000
1.3.1 | 3 | test we unit | 30,000
1.3.2 | 2 | test web system | 15,000
1.4 | 2 | feed& deliver &report | 10,000

## Slide 11: Net Work

## Slide 12: Baseline Budget
ID | Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 | 40,000$ | 6,000 | 6,000 | 6,000 | 2,000 | 6,000 | 7,000 | 7,000 |  |  |  |  |  |  |  | 
1.2.1 | 20,000$ |  |  |  |  |  |  |  | 20,000 |  |  |  |  |  |  | 
1.2.2 | 45,000$ |  |  |  |  |  |  |  | 25,000 | 20,000 |  |  |  |  |  | 
1.2.3 | 40,000$ |  |  |  |  |  |  |  | 9,000 | 20,000 | 11,000 |  |  |  |  | 
1.3.1 | 30,000$ |  |  |  |  |  |  |  |  |  |  | 5,000 | 15,000 | 10,000 |  | 
1.3.2 | 15,000$ |  |  |  |  |  |  |  |  |  |  | 7,000 | 8,000 |  |  | 
1.4 | 10,000 |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,000 | 5,000
Total | 200,000$ | 6,000 | 6,000 | 6,000 | 2,000 | 6,000 | 7,000 | 7,000 | 54,000 | 40,000 | 11,000 | 12,000 | 23,000 | 10,000 | 5,000 | 5,000
Commutative |  | 6,000 | 12,000 | 18,000 | 20,000 | 26,000 | 33,000 | 40,000 | 94,000 | 134,000 | 145,000 | 157,000 | 180,000 | 190,000 | 195,000 | 200,000
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15

## Slide 13: Time phase

## Slide 14: Responsibility Matrix Responsibility of each team
Tasks | Abdullah | Abdulrahman
Initiation | S | R
soft& hard ware install | S | R
soft& hard ware design | R | S
soft& hard ware implement | R | S
test we unit | S | R
test web system | R | S
feed&deliver&report | S | R
Responsibility | R
Supportive | S
Responsibility Matrix
Responsibility of each team

## Slide 15: Resource
ID | RES | DUR | ES | LF | SL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 | 2p | 7 | 0 | 7 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
1.2.1 | 2p | 1 | 7 | 10 | 2 |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  | 
1.2.2 | 2p | 2 | 7 | 11 | 2 |  |  |  |  |  |  |  | 2 | 2 |  |  |  |  |  |  |  |  | 
1.2.3 | 1p | 3 | 7 | 10 | 0 |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 
1.3.1 | 1p | 3 | 10 | 13 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  | 1 |  |  |  | 
1.3.2 | 1p | 2 | 10 | 13 | 1 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  | 
1.4 | 1p | 2 | 13 | 15 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  | 1
Total Resource Load |  |  |  |  |  | 2p | 2p | 2p | 2p | 2p | 2p | 2p | 5p | 3p | 1p | 2p |  | 2p |  | 1p |  | 1p | 1p
Resource Available |  |  |  |  |  | 5p | 5p | 5p | 5p | 5p | 5p | 5p | 5p | 5p | 5p | 5p |  | 5p |  | 5p |  | 5p | 5p
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15

## Slide 16: Risks
1-system break down
2- customer information steel
3-customer enter a wrong info
4-one of team leaves
5- financial viability
6- System Reliability